## Project Schedule
Task Name | Resource | Duration | Start | Finish
Requirements Phase | NA | 0 | 2021-02-01 | 2021-02-01
Scope | Sam | 2 | 2021-02-02 | 2021-02-04
Find second dataset for mapping | All | 2 | 2021-02-02 | 2021-02-04
Data Engineering Phase |  | 0
Copy code from "Java Mini" as our starter code |  | 0
Convert the.csv file to to JSON and read in to code |  | 0
Name our variables from the dataset and update variables in the code |  | 0
Code Development and Design Phase |  | 0
Sketch dashboard design |  | 0
Code the index file to include the div's from our dashboard design (TBD) |  | 0
Populate drop downs with appropriate fields and add event listener |  | 0
Configure the default view |  | 0
0
0
Visualization Development Phase |  | 0
Visualization 1 |  | 0
Visualization 2 |  | 0
Visualization 3 |  | 0
Visualization 4 |  | 0
Visualization 5 |  | 0
Insert visualizations into "master file" |  | 0
Deployment |  | 0
Git commit |  | 0
Deploy to Heroku |  | 0
Note on A12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The instructions for the step are available at https://zoom.us/rec/play/Qw04fYFMUsRIXLak1TvswfIDqmPwoV16FvN4WGobshjUTySXNjvFWznQNB5b5pZgs6qRZCUK2SbFpBXi.yUvOevLRk7398GsV ... 4:33 in the video

## Team Roles
Team Role Sign Up
Sandra Hall
Tsegaye Mirach
Fraol Abebe
Sam Smith
Alejandra Herbas
Options
Project Manager
UX/UI & Quality Engineer
Data Engineer
Data Visualization Analyst
GIS Web Mapping Analyst
Researcher

## Questions and Visualizations
Question | Should we include this in our dashboard? Y/N | Visualization Type
What are the characteristics of top performers?
What factors correlate to a higher degree of job satisfaction?
What are the criteria that predict who might stay with the company longest?
How does salary effect job satisfaction?
How does salary effect employee performance rating?
Level of job satisfaction | Y | Meter/Needle
Average salary by division
Average salary by gender
Total of all salaries
Average salary overall
Percentage of employees that are currently at top level of performance
Average employee seniority
Percentage of employee attrition in the current data
Employee performance by specified age groups
Employee performance by gender
Employee performance by years with the company (in bins)
Employee performance by marital status
Employee performance by education level
Male vs. Female ratio by division
Data analysis questions are above the gray line, whereas some data we could showcase as sort of an "overview of where we are" is below the gray line. Just some ideas :)

## Project 3 Ideas
ID | Project 3 Models
1 | Implement a "pay-grade" salary model (similar to the GS system seen in the federal government) that would use the analysis we have already conducted as well as the conclusions to evaluate if having a more structured salary model across the board could positively influence job satisfaction.
Business Solution 1: Possibly could close any presence of a gender wage gap.
Business Solution 2: Would grow employee trust in their employer through transparency and structure. Could positively influence length of time an employee remains with their employer.
2 | Statistical Test: What are the top three drivers of employee attrition? Measure statistical correlation in relevant dependent variables.
3 | General Idea: Tie a monetary value to our proposed solutions--ie. Return on Investment (ROI) such as "pay a higher salary now for X employee but over 15 years save Y in training/education funding". This could add a financial analysis to the project and our own portfolios.
4 | Find the top-indicators of a top peforming employee through exposing which variables in our dataset hold the strongest correlation.
Business Solution 1: Build a product we would hypothetically give to recruiters enabling them to "drag and drop in" submitted resumes that would search for these indicators and return the top 5 or so matching the specified criteria. We could build the front end using Javascript and use JSON on the backend to filter through the text in resumes.