## Project Schedule
Task Name | Resource | Duration | Start | Finish
Requirements Phase | NA | 0 | 2021-02-01 | 2021-02-01
Proposal/Scope | Sam | 2 | 2021-02-02 | 2021-02-04
Find a second data set to use for mapping | All | 2 | 2021-02-02 | 2021-02-04
Data Engineering Phase |  | 0
Copy code from "Java Mini" as our starter code | All | 0 | 2021-02-04 | 2021-02-04
Convert the.csv file to to JSON and read in to code | All | 0 | 2021-02-04 | 2021-02-04
Read dataset into group AWS | All | 0 | 2021-02-04 | 2021-02-04
Read dataset into MySQL Workbench | All | 0 | 2021-02-04 | 2021-02-04
Name our variables from the dataset and update variables in the code | All | 0 | 2021-02-04 | 2021-02-04
Code Development and Design Phase
Sketch dashboard design | Sandra |  | 2021-02-04
Code the index file to include the div's from our dashboard design
Populate drop downs with appropriate fields and add event listener
Configure the default view
Visualization Development Phase
Visualization 1
Visualization 2
Visualization 3
Visualization 4
Visualization 5
Insert visualizations into "master file"
Deployment
Git commit
Deploy to Heroku
Note on A14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The instructions for the step are available at https://zoom.us/rec/play/Qw04fYFMUsRIXLak1TvswfIDqmPwoV16FvN4WGobshjUTySXNjvFWznQNB5b5pZgs6qRZCUK2SbFpBXi.yUvOevLRk7398GsV ... 4:33 in the video

## Team Roles
Team Role Sign Up
Sandra Hall |  | UX/UI & Quality Engineer
Tsegaye Mirach |  | Researcher
Fraol Abebe |  | Data Engineer
Sam Smith |  | Sam Smith
Alejandra Herbas |  | Project Manager
| Options |  | Assigned
| Project Manager |  | Alejandra Herbas
| UX/UI & Quality Engineer |  | Sandra Hall
| Data Engineer |  | Fraol Abebe
| Data Visualization Analyst |  | Everyone
| GIS Web Mapping Analyst |  | Sam Smith
| Researcher |  | Tsegaye Mirach
| Machine Learning Engineer |  | Project 3

## Questions and Visualizations
Question | Should we include this in our dashboard? Y/N | Visualization Type
What are the characteristics of top performers?
What factors correlate to a higher degree of job satisfaction?
What are the criteria that predict who might stay with the company longest?
How does salary effect job satisfaction?
How does performance rating affect salary?
How does marital status affect job satisfaction?
What was the performance category of employees who left the company?
How is job satisfaction affected by commuting distance?
How is job satisfaction affected by business travel?
How is job satisfaction affected by overtime?
How is job satisfaction affected by job role?
How does the education level affect the monthly rate/salary?
How does the department affect the monthly rate/salary?
How does gender affect salary overall in the company?
How does gender affect salary in each department of the company?
How does gender affect job satisfaction within each department?
How does your years in current role affect your job satisfaction?
How does your years since last promotion affect job satisfaction?
How does your years at the company affect your job satisfaction?
How does your age affect job satisfaction?
How does your department affect your job satisfaction?
How does last salary hike affect performance rating?
How does last salary hike affect job satisfaction?
Level of job satisfaction | Y | Meter/Needle
Average salary by division
Average salary by gender
Average age of the employees
Total of all salaries
Average salary overall
Percentage of employees that are currently at top level of performance
Average employee seniority
Percentage of employee attrition in the current data
Employee performance by specified age groups
Employee performance by gender
Employee performance by years with the company (in bins)
Employee performance by marital status
Employee performance by education level
Male vs. Female ratio by division

## Project 3 Ideas
ID | Project 3 Models
1 | Implement a "pay-grade" salary model (similar to the GS system seen in the federal government) that would use the analysis we have already conducted as well as the conclusions to evaluate if having a more structured salary model across the board could positively influence job satisfaction.
Business Solution 1: Possibly could close any presence of a gender wage gap.
Business Solution 2: Would grow employee trust in their employer through transparency and structure. Could positively influence length of time an employee remains with their employer.
2 | Statistical Test: What are the top three drivers of employee attrition? Measure statistical correlation in relevant dependent variables.
3 | General Idea: Tie a monetary value to our proposed solutions--ie. Return on Investment (ROI) such as "pay a higher salary now for X employee but over 15 years save Y in training/education funding". This could add a financial analysis to the project and our own portfolios.
4 | What factors hold the strongest correlation to our top performers?
Business Solution 1: Use this info to create a "product" we would hypothetically deliver to the Recruiting team, that could automate filtering through resumes with a "drag and drop" feature into a form we create with javascript and possibly through using JSON, to pull the resumes first that hold the characteristics we find are consistent among top performers in our company.