## Project Schedule
Placement | Task Name | Resource | Duration | Start | Finish
| Requirements Phase | NA | 0 | 2021-02-01 | 2021-02-01
| Proposal/Scope | Sam | 2 | 2021-02-02 | 2021-02-04
| Find a second data set to use for mapping | All | 2 | 2021-02-02 | 2021-02-04
| Data Engineering Phase |  | 0
| Copy code from "Java Mini" as our starter code | All | 0 | 2021-02-04 | 2021-02-04
| Convert the.csv file to to JSON and read in to code | All | 0 | 2021-02-04 | 2021-02-04
| Read dataset into group AWS | All | 0 | 2021-02-04 | 2021-02-04
| Read dataset into MySQL Workbench | All | 0 | 2021-02-04 | 2021-02-04
| Name our variables from the dataset and update variables in the code | All | 0 | 2021-02-04 | 2021-02-04
| Code Development and Design Phase |  | 0
| Sketch dashboard design | All |  | 2021-02-04
| Code the index file to include the div's from our dashboard design | All |  | 2020-02-05
| Populate drop downs with appropriate fields and add event listener | Fraol & Alejandra | 0 | 2020-02-05 | 2020-02-05
| Configure the default view | All |  | 2020-02-05
1 | Set up the Title Image Carasoul: "Recruit and Retain", About the Staff, Our Mission Statement
2 | Move 4 images (summary stats) to show under the title slot: Total Employees, Age Box Plot, Average Performance Rating, Average Employee Satisfaction
3 | Next Section: Employee Satisfaction by Department - "Happiness Meter"
4 | Bar graph: Showing overall performance rating by department and broken down beside it by job role. Place department dropdown with this.
Top of page in overview: Pie Chart on each category of the satisfaction rating for the whole dataset.
Top of page in overview: Box plot showing summary statistics of ages.
Add statistical correlation info below related to relationship between employee satisfaction by dept and employee job performance by dept.
Line Graph on what contributes to salary hike - Performance Rating, Years in Current Role, Years with Current Manager - possibly use drop down showing education/education level.
Scatter Plot on what contributes to attrition - show attrition yes and attition no in the legend showing two different color codes. Build Y-axis to show Job Involvement X-axis years since last promotion.
Funnel chart to show employee attrition?
Develop the CSS: Colors, Background, Etc.
Visualization Development Phase
Visualization 1
Visualization 2
Visualization 3
Visualization 4
Visualization 5
Insert visualizations into "master file"
Deployment
Git commit
Deploy to Heroku
Note on B14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The instructions for the step are available at https://zoom.us/rec/play/Qw04fYFMUsRIXLak1TvswfIDqmPwoV16FvN4WGobshjUTySXNjvFWznQNB5b5pZgs6qRZCUK2SbFpBXi.yUvOevLRk7398GsV ... 4:33 in the video

## Team Roles
Team Role Sign Up
Sandra Hall |  | UX/UI & Quality Engineer
Tsegaye Mirach |  | Researcher
Fraol Abebe |  | Data Engineer
Sam Smith |  | Sam Smith
Alejandra Herbas |  | Project Manager
| Options |  | Assigned
| Project Manager |  | Alejandra Herbas
| UX/UI & Quality Engineer |  | Sandra Hall
| Data Engineer |  | Fraol Abebe
| Data Visualization Analyst |  | Everyone
| GIS Web Mapping Analyst |  | Sam Smith
| Researcher |  | Tsegaye Mirach
| Machine Learning Engineer |  | Project 3

## Questions and Visualizations
Question | Should we include this in our dashboard? Y/N | Visualization Type
What are the characteristics of top performers?
What factors correlate to a higher degree of job satisfaction?
What are the criteria that predict who might stay with the company longest?
How does salary effect job satisfaction?
How does performance rating affect salary?
How does marital status affect job satisfaction?
What was the performance category of employees who left the company?
How is job satisfaction affected by commuting distance?
How is job satisfaction affected by business travel?
How is job satisfaction affected by overtime?
How is job satisfaction affected by job role?
How does the education level affect the monthly rate/salary?
How does the department affect the monthly rate/salary?
How does gender affect salary overall in the company?
How does gender affect salary in each department of the company?
How does gender affect job satisfaction within each department?
How does your years in current role affect your job satisfaction?
How does your years since last promotion affect job satisfaction?
How does your years at the company affect your job satisfaction?
How does your age affect job satisfaction?
How does your department affect your job satisfaction?
How does last salary hike affect performance rating?
How does last salary hike affect job satisfaction?
Level of job satisfaction | Y | Meter/Needle
Average salary by division
Average salary by gender
Average age of the employees
Total of all salaries
Average salary overall
Percentage of employees that are currently at top level of performance
Average employee seniority
Percentage of employee attrition in the current data
Employee performance by specified age groups
Employee performance by gender
Employee performance by years with the company (in bins)
Employee performance by marital status
Employee performance by education level
Male vs. Female ratio by division

## Project 3 Ideas
ID | Project 3 Models
1 | Implement a "pay-grade" salary model (similar to the GS system seen in the federal government) that would use the analysis we have already conducted as well as the conclusions to evaluate if having a more structured salary model across the board could positively influence job satisfaction.
Business Solution 1: Possibly could close any presence of a gender wage gap.
Business Solution 2: Would grow employee trust in their employer through transparency and structure. Could positively influence length of time an employee remains with their employer.
2 | Statistical Test: What are the top three drivers of employee attrition? Measure statistical correlation in relevant dependent variables.
3 | General Idea: Tie a monetary value to our proposed solutions--ie. Return on Investment (ROI) such as "pay a higher salary now for X employee but over 15 years save Y in training/education funding". This could add a financial analysis to the project and our own portfolios.
4 | What factors hold the strongest correlation to our top performers?
Business Solution 1: Use this info to create a "product" we would hypothetically deliver to the Recruiting team, that could automate filtering through resumes with a "drag and drop" feature into a form we create with javascript and possibly through using JSON, to pull the resumes first that hold the characteristics we find are consistent among top performers in our company.